## AHMAD HQ — DASHBOARD
AHMAD HQ — OPERATING HOME
MONTH PLAN\nOutcomes • calendar • close |  | THIS WEEK\nCommitments • deadlines |  | EDIBLE\nStore pulse • controls |  | GARDENIA'S\nLaunch • sales funnel |  | CALLS / FOLLOW-UP\nContacts • next touch |  | PEOPLE\nSchedule • capacity
MANAGEMENT PULSE — WHAT NEEDS ATTENTION
[5 empty] | SUN | MON | TUE | WED | THU | FRI | SAT
CRITICAL MOVES\n6 open |  | WAITING / BLOCKED\n0 items |  | DECISIONS\n1 | 30 | 31 | 1 | 2 | 3 | 4 | 5
[5 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12
[5 empty] | 13 | 14 | 15 | 16 | 17 | 18 | 19
[5 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26
[5 empty] | 27 | 28 | 29 | 30 | 1 | 2 | 3
THIS WEEK — 6 MEANINGFUL MOVES
FUNCTION / PROJECT | WHAT MUST HAPPEN | OWNER | DUE | STATUS | WHY / RESULT | WAITING / ESCALATE
Gardenia's Fire | Confirm sellable offer is ready from Emmanuel's real-life process; capture only price/cost/margin or constraints needed for selling/management | Emmanuel | 2026-08-31 | In Progress | Sales readiness / management economics without duplicating product development
Gardenia's Fire | Build/confirm target account list | Emmanuel | 2026-09-01 | Open | Create qualified sales pipeline
Gardenia's Fire | Begin outreach and schedule tastings | Emmanuel | 2026-09-04 | Open | Create tastings / standing-account conversations
Edible Operations | Execute labor schedule correction and verify effect | Emmanuel | 2026-09-02 | In Progress | Bring labor productivity toward target | • ESCALATE
Finance & Office | Confirm books/reconciliations/evidence current for weekly close | Moises | 2026-09-04 | Open | Reliable finance close / no silent issue | • ESCALATE
My Work | xfgnxfm | xfmfhm | xmh | Open | xfmhxfhm
OPERATING AREAS — PURPOSE • CURRENT STATE • WHAT'S NEXT
AREA | FOCUS | OWNER | PURPOSE / OUTCOME | CURRENT MILESTONE | WHAT'S NEXT | STATUS
Edible Operations | MAINTAIN | Emmanuel | Keep store stable while correcting sales/labor/service economics | Correct current sales/labor trend | Verify schedule/lead behavior effect | Active
Gardenia's Fire | PUSH | Emmanuel | Prove offer and create repeatable local corporate standing-order sales | Product proof + outreach/tastings | Finalize costing, target list, outreach, tastings | Active
Finance & Office | PUSH | Moises | Keep books, cash, obligations, evidence, and office controls current | Reliable weekly close / exceptions | Establish clean weekly close with evidence | Active
Podcast / Legacy | PUSH | Ahmad | Create and publish meaningful podcast/video work while retaining legacy material | Current episode/video progression | Move next video/episode to executable step | Active
People / Systems | MAINTAIN | Emmanuel | Clear ownership, capacity, follow-through, and system improvement | Monday-ready operating rhythm | Operate Phase 1 and remove duplicate reporting | Active
Iron Marks / Iron March | PARK | TBD | Keep visible without stealing capacity until intentionally activated | Define offer/owner/test/capacity before PUSH | Remain parked until activation decision | Parked
Ahmad Personal Finance / Life | PUSH | Ahmad / Moises / Emmanuel | Protect personal stability: money in/out, obligations, credit, personal admin, decisions | Basic visibility + recurring control | Moises maintains back-end; Emmanuel coordinates completeness/exceptions; Ahmad decides | Build
QUICK DOORS — WORK FROM HERE, DON'T HUNT FOR FILES
EDIBLE DETAIL\nDaily • weekly • month close |  |  | FINANCE DETAIL\nBooks • reconciliations • evidence |  |  | GARDENIA'S FILES\nPlan • products • target lists |  |  | v3 BOARD\nPresentation reference

## HQ_PLANS
Plan ID | Period Type | Period Key | Business / Area | Objective / Priority | Critical Move? | Lead Behavior | Lead Behavior Actual | Expected Outcome | Owner | Due | Status | Result | Evidence / Source

## HQ_REGISTRIES
Registry Type | Business / Area | Name | Purpose / Responsibility | Owner | Cadence / Stage | Status | Backup / Contact | Source / Evidence | Notes

## HQ_PEOPLE
Name | Email | Role | Function / Area | Availability | Responsibilities | Backup | Priority Load | Coverage Status | Training Status | Active? | Notes

## HQ_REQUESTS
Request ID | Date | Business / Area | Request Type | Request / Issue | Severity / Urgency | Owner | Approval Status | Status | Due | Evidence / Photo | Resolution

## HQ_SOURCE_MAP
Business / Area | Metric / Control | Input Owner | Authoritative Source | Frequency | Evidence Location | Calculation / Rule | Destination Screen | Status | Last Verified
Shared Management | Weekly priorities / Critical Moves / owned work | Emmanuel | AHMAD HQ — WORK DESK — UPDATE + THIS WEEK | Weekly / live | https://docs.google.com/spreadsheets/d/1_zaAT-zqEQhwTW2ZNRLSnH8Peed7zZTzi3kd0RUHQRQ/edit | One management work record carries owner, due, status, result, evidence, blocker and escalation; role views compress from it. | THIS WEEK; EMMANUEL — HOME; AHMAD — CONTROL | VERIFIED INTERNAL MANAGEMENT SOURCE | 2026-09-01
Finance & Office | Weekly finance close / control status / exceptions | Moises | OFFICE FINANCE — LIVE CONTROL SYSTEM — REVISED Aug 2026 | Weekly | https://docs.google.com/spreadsheets/d/1zrY3SOQiF2g8A_7z4ynA9mVnM7_qsvS8eBsebBRplmc/edit | Weekly Review + Evidence Register + underlying account detail; one completion should feed management review, not parallel duplicate checkmarks. | MOISES — HOME; HQ_CHECKLIST_RUNS; RESULTS & EXCEPTIONS | VERIFIED STRUCTURE / LIVE USE EARLY | 2026-09-01
Finance & Office | Books current / cash / A-P / A-R / payroll / reconciliations | Moises | QuickBooks + banks/cards/merchant/payroll source systems; Finance control workbook is management-control layer | Weekly / monthly | Finance control workbook + linked evidence/Drive | Actuals must reconcile to transactional source; HQ receives current-through date, status, variance, exception and material decision. | HQ_KSI; HQ_TARGETS; MOISES — HOME; AHMAD — CONTROL | SOURCE ROLE VERIFIED / CONNECTION NOT YET VERIFIED | 2026-09-01
Edible | Store operating controls / Week Close / operational exceptions | Store Lead → Emmanuel | Edible Hackensack — Store Operations Control System — v3 — Aug 2026 | Daily / weekly / monthly | https://docs.google.com/spreadsheets/d/1_qBjYd0F4BYYTxLMJjEZbQynBdHH5JGe83-U7nheJOE/edit | Detailed work stays in Edible operating system; Week Close/results/exceptions roll upward; HQ is not a second store checklist. | EDIBLE — OPERATE; HQ_CHECKLIST_RUNS; RESULTS & EXCEPTIONS | VERIFIED STRUCTURE / ADOPTION EARLY | 2026-09-01
Edible | Sales / orders / average ticket | Emmanuel / Store | Edible franchise/POS source; weekly management report is current reporting layer | Weekly | https://docs.google.com/spreadsheets/d/1Y1auf1Xc_wzNI4vh90JABYfC7HoifdcC/edit | POS is transactional truth; management report/HQ must preserve week, comparable period, actual, target and variance. | EDIBLE — OPERATE; HQ_TARGETS; HQ_KSI | REPORT SOURCE VERIFIED / POS CONNECTION NOT VERIFIED | 2026-09-01
Edible | Labor / COGS / waste / refunds | Emmanuel + Moises | Payroll/timeclock + POS/franchise + accounting sources; Edible KPI/Week Close is management layer | Weekly | Edible v3 + Finance evidence | Use source actuals; compare to target; exception when materially outside standard; preserve cause/action. | EDIBLE — OPERATE; HQ_KSI; RESULTS & EXCEPTIONS | SOURCE MODEL VERIFIED / WIRING NOT VERIFIED | 2026-09-01
Gardenia's Fire | Launch priorities / field activity / weekly conversion learning | Emmanuel | HQ Work Desk + Month Plan + Emmanuel weekly/September operating control | Daily / weekly | AHMAD HQ Phase 1 Core + current operating schedule/control materials | Plan work in HQ; field execution produces coded outcomes, owner/date, follow-up, conversion learning and next move. | GARDENIA — OPERATE; THIS WEEK; EMMANUEL — HOME | VERIFIED MANAGEMENT SOURCE / LIVE SALES DATA EARLY | 2026-09-01
Gardenia's Fire | Prospects / contacts / tastings / proposals / standing-account pipeline | Emmanuel / revenue owner | Shopify planned commerce/order/customer source + accounting for financial truth; Emmanuel's real-life operating process owns product development/testing | Live / weekly / monthly | Shopify/QuickBooks once configured; real-life operating evidence until then | Commerce/accounting own transactions and financial truth; Emmanuel's operating process owns product development. HQ receives sellable-readiness state, revenue, orders, repeat/standing accounts, decision-useful margin/capacity, exceptions and decisions. | GARDENIA — OPERATE; HQ_TARGETS; HQ_KSI; AHMAD — CONTROL | PLANNED SOURCE / PRODUCT-DEVELOPMENT BOUNDARY CORRECTED | 2026-09-03
Gardenia's Fire | Orders / standing cadence / revenue / repeat / margin | Emmanuel + Moises | Shopify planned commerce/order/customer source + accounting for financial truth | Live / weekly / monthly | Shopify/QuickBooks once configured; HQ product/costing currently interim | Commerce system owns transactions; HQ receives revenue, orders, repeat/standing accounts, margin and exceptions. | GARDENIA — OPERATE; HQ_TARGETS; HQ_KSI; AHMAD — CONTROL | PLANNED SOURCE / NOT READY | 2026-09-01
Ironmark | Pilot lane / providers / leads / completed jobs / economics / quality | Emmanuel / assigned revenue owner | Actual schedules/payroll/HR source where applicable; PEOPLE & CAPACITY is management snapshot; HQ_ACCESS is permission truth; HQ_PEOPLE only for consequential role/coverage state if needed | Weekly / on change | Authoritative schedule/HR source + AHMAD HQ Phase 1 Core | Do not maintain a duplicate full roster/schedule in HQ. Surface only role ownership, current capacity/conflict, backup/coverage, material availability change and management exception. | PEOPLE & CAPACITY; role Homes; HQ_ACCESS | BOUNDARY CORRECTED — MANAGEMENT SNAPSHOT, NOT HR/SCHEDULE SYSTEM | 2026-09-03
People & Systems | Role access / management depth / current capacity | Emmanuel | HQ_ACCESS + PEOPLE & CAPACITY; HQ_PEOPLE is intended durable people register | Weekly / on change | AHMAD HQ Phase 1 Core | Separate confirmed roles/capacity from provisional roles; permissions must match management level and sensitive-area restrictions. | PEOPLE & CAPACITY; role Homes; HQ_ACCESS | PARTIAL / HQ_PEOPLE NOT POPULATED | 2026-09-01
Podcast / Legacy | Asset stage / review / edit / retain / publish next action | Ahmad + Emmanuel | Google Drive canonical podcast/video folders + HQ_PODCAST management register | Weekly / per asset | Drive source assets; HQ_PODCAST intended management state | Drive owns files; HQ owns stage, owner, due, current/future-use decision and next action. | THIS WEEK; HQ_PODCAST; EMMANUEL — HOME | SOURCE MODEL VERIFIED / HQ REGISTER NOT POPULATED | 2026-09-01
Personal / Ahmad | Bills / obligations / recurring charges / deadlines / material exceptions | Moises + Emmanuel | Bank/provider/account sources + Drive evidence; HQ_PERSONAL_REGISTER is management-control layer | Weekly | Source map/evidence still to be established | Do not recreate bookkeeping; surface upcoming obligations, money movement, deadlines, exceptions and decisions to Ahmad. | AHMAD — CONTROL; MOISES — HOME; HQ_PERSONAL_REGISTER | NOT YET POPULATED / SOURCE VERIFICATION REQUIRED | 2026-09-01

## HQ_REFERENCE_LIBRARY
Business / Area | Reference Type | Title | Current? | Audience / Role | Owner | Source / Drive Link | Supersedes / Replaces | Status | Notes

## HQ_TRAINING
Business / Area | Role / Person | Capability / Training | Required? | Status | Evidence / Guide | Owner | Due | Last Verified | Notes

## HQ_FINANCE_REGISTER
Register Type | Entity / Property | Account / Policy / Vendor / Tax | Status | Amount / Balance | Effective / Filing / Renewal | Due / Next Date | Owner | Source / Evidence | Next Action | Notes
Credit Line | EA Hackensack | Chase LOC | STALE / RECONCILE REQUIRED | 121412.5 | Source dated 2025-09-25 | Verify now | Moises | Balances (Updated 01.01.26) — EA HACKENSACK tab | Reconcile to Chase documents + QuickBooks + current statement | Working balance only; Chase litigation/credit-line correspondence now active.
Credit Card | EA Hackensack | Chase card | STALE / RECONCILE REQUIRED | 15243.55 | Source dated 2025-09-25 | Verify now | Moises | Balances (Updated 01.01.26) — EA HACKENSACK tab | Reconcile to card statement + QuickBooks | Working balance.
A/P | EA Hackensack | Plainfield Produce | STALE / RECONCILE REQUIRED | 1191.48 | Undated row in working balance sheet | Verify now | Moises | Balances (Updated 01.01.26) — EA HACKENSACK tab | Check QuickBooks A/P aging/vendor detail and vendor statement | Potential open vendor balance.
Credit Line | BMS Office | Chase LOC | STALE / RECONCILE REQUIRED | 70959.1 | Source dated 2025-09-25 | Verify now | Moises | Balances (Updated 01.01.26) — BMS OFFICE tab | Reconcile to Chase documents + QuickBooks + current statement | Working balance.
Credit Line | Buyahka | First Commerce LOC | STALE / RECONCILE REQUIRED | 371555.65 | Source dated 2025-09-25 | Verify now | Moises | Balances (Updated 01.01.26) — BUYAHKA tab | Reconcile to First Commerce statements/loan docs + QuickBooks | Sheet notes approx. $3,443 available and no principal paid as of source date.
Credit Card | Five Star Bath | Provident + Shell | STALE / RECONCILE REQUIRED | 33664.79 | Source dated 2025-09-25 | Verify now | Moises | Balances (Updated 01.01.26) — FIVE STAR BATH tab | Reconcile cards to statements + QuickBooks | Provident 33,329.67 + Shell 335.12.
A/P | Five Star Bath | Five Star Corp + Tom + WXYZ Scripps | STALE / RECONCILE REQUIRED | 42287.56 | Mixed/older source dates | Verify now | Moises | Balances (Updated 01.01.26) — FIVE STAR BATH tab | Check QuickBooks A/P aging, vendor statements and dispute/payment status | Includes Five Star Corp 22,187.56; accountant 1,500; WXYZ 18,600.
Personal Credit Card | Ahmad Personal / business-use overlap | Capital One cards | STALE / RECONCILE REQUIRED | 51839.37 | Source dated 2025-09-25 | Verify now | Moises + Ahmad | Balances (Updated 01.01.26) — AHMAD PERSONAL tab | Reconcile to current Capital One statements + QuickBooks allocations/reimbursements | Sheet says one card used for Edible; another used for personal and FSBS.
Cash Plan | Buyahka | Sep-Dec 2026 forward cash/distribution plan | ACTIVE WORKING PLAN / VERIFY ACTUALS | See source | Sep-Dec 2026 | Monthly | Moises | Buyahka Compensation | Reconcile actual receipts/payments monthly to bank + QuickBooks | Shows Flower Shop and NY Elevators inflows, recurring property costs, loan payment and planned payments to Ahmad/Hackensack reimbursement.

## HQ_PODCAST
Item ID | Episode / Asset | Stage | Item Type | Owner | Due | Status | Source / Drive Link | Current / Future Use | Publish Target / Platform | Next Action | Notes

## HQ_PERSONAL_REGISTER
Register Type | Item / Account / Policy | Status | Amount | Expected / Renewal / Due | Owner | Source / Evidence | Next Action | Exception? | Notes

## HQ_CUSTOMER_FOLLOWUP
Follow-up ID | Date | Business | Customer / Recipient | Trigger / Segment | Priority | Owner | Due | Status | Next Action | Result | Source / Evidence

## HQ_NOTIFICATION_RULES
Rule ID | Area | Trigger | Severity | Delivery | Recipient / Role | Active? | Last Fired | Notes

## HQ_KSI
Business / Area | Metric / Indicator | Owner | Cadence | Authoritative Source | Threshold / Target | Direction | Current | Status | Last Updated | Next Move

## HQ_GARDENIA_PIPELINE
Account / Prospect | Stage | Contact / Company | Last Contact | Next Follow-up | Tasting / Sample | Standing Cadence | Revenue / Value | Risk | Owner | Source / Evidence | Notes

## HQ_SYSTEM_ACCESS
System / Account | User / Role | Business / Area | Access Level | Owner / Admin | Status | Last Verified | Source / Login Page | Notes

## HQ_GARDENIA_PRODUCT
Product / Test | Standard / Specification | Test Status | Unit Cost | Price | Target Margin | Actual Margin | Open Assumption / Issue | Owner | Source / Evidence | Last Updated

## HQ_CUSTOMER_ISSUES
Date | Week | Year | Business | Issue Type | Customer | Reason / Theme | Amount / Value | Severity | Recovery / Action | Owner | Status | Source / Evidence

## HQ_ACCESS
Email | Name | Role | Area | Active? | Can See All? | Notes
ahmad@wolfventuresnj.com | Ahmad | Executive Owner | All | Yes | Yes | Full owner visibility
emmanuel@wolfventuresnj.com | Emmanuel Nwachukwy | Coordinator / Integrator | Shared Management; Edible; Gardenia's Fire; Finance & Office; Legacy Closeout; Buyahka / Property; People & Systems; Podcast / Legacy; Iron Marks | Yes | No | Multi-area operating access; Personal / Ahmad intentionally excluded.
bookkeeper@wolfventuresnj.com | Moises A. San Miguel | Finance / Bookkeeping | Finance & Office; Edible; Gardenia's Fire; Legacy Closeout; Buyahka / Property | Yes | No | Finance/data/control access; Personal / Ahmad intentionally excluded.

## HQ_CHECKLIST_DEFS
Checklist ID | Business | Area | Checklist Name | Cadence | Owner Role | Required? | Evidence Required? | Active? | Sort
ED-OPEN | Edible | Store | Opening Checklist | DAILY | Store Lead | Yes | No | No | 10
ED-PROD | Edible | Store | Production Readiness | DAILY | Store Lead | Yes | No | No | 20
ED-QA | Edible | Store | Food Safety / Quality | DAILY | Store Lead | Yes | Yes | No | 30
ED-CLEAN | Edible | Store | Cleaning / Sanitation | DAILY | Store Team | Yes | No | No | 40
ED-INV | Edible | Store | Inventory / Supplies | DAILY | Store Lead | Yes | No | No | 50
ED-CUST | Edible | Store | Customer Issues / Guest Connect | DAILY | Store Lead | Yes | Yes | No | 60
ED-CLOSE | Edible | Store | Closing Checklist | DAILY | Store Lead | Yes | Yes | No | 70
ED-WEEK | Edible | Management | Edible Weekly Management Review | WEEKLY | Coordinator | Yes | Yes | No | 100
FI-WEEK | Finance & Office | Management | Finance Week Close | WEEKLY | Finance | Yes | Yes | No | 110
HQ-WEEK | Shared Management | Management | HQ Week Close | WEEKLY | Coordinator | Yes | Yes | Yes | 120
HQ-MONTH | Shared Management | Management | HQ Month Close | MONTHLY | Coordinator | Yes | Yes | Yes | 130
GF-WEEK | Gardenia's Fire | Management | Gardenia Weekly Review | WEEKLY | Coordinator | Yes | Yes | Yes | 140
LC-WEEK | Legacy Closeout | Management | Legacy Closeout Weekly Review | WEEKLY | Coordinator | Yes | Yes | Yes | 150

## HQ_CHECKLIST_ITEMS
Checklist ID | Item ID | Item | Required? | Evidence Required? | Escalate On Fail? | Sort
ED-OPEN | ED-OPEN-01 | Front/store opening condition | Yes | No | Yes | 10
ED-OPEN | ED-OPEN-02 | Phones / tablets / POS ready | Yes | No | Yes | 20
ED-OPEN | ED-OPEN-03 | Fruit / ingredients readiness | Yes | No | Yes | 30
ED-OPEN | ED-OPEN-04 | Production plan reviewed | Yes | No | Yes | 40
ED-OPEN | ED-OPEN-05 | Delivery / pickup schedule reviewed | Yes | No | Yes | 50
ED-OPEN | ED-OPEN-06 | Staff coverage confirmed | Yes | No | Yes | 60
ED-OPEN | ED-OPEN-07 | Cleaning / sanitation opening check | Yes | No | Yes | 70
ED-OPEN | ED-OPEN-08 | Critical supplies available | Yes | No | Yes | 80
ED-PROD | ED-PROD-01 | Orders prioritized by promise time | Yes | No | Yes | 10
ED-PROD | ED-PROD-02 | Fruit prep plan ready | Yes | No | Yes | 20
ED-PROD | ED-PROD-03 | Chocolate / ingredients ready | Yes | No | Yes | 30
ED-PROD | ED-PROD-04 | Packaging / containers ready | Yes | No | Yes | 40
ED-PROD | ED-PROD-05 | Delivery orders staged | Yes | No | Yes | 50
ED-PROD | ED-PROD-06 | Special instructions reviewed | Yes | No | Yes | 60
ED-QA | ED-QA-01 | Refrigeration / cold holding acceptable | Yes | Yes | Yes | 10
ED-QA | ED-QA-02 | Fruit quality acceptable | Yes | No | Yes | 20
ED-QA | ED-QA-03 | Chocolate / product quality acceptable | Yes | No | Yes | 30
ED-QA | ED-QA-04 | Sanitation standard met | Yes | Yes | Yes | 40
ED-QA | ED-QA-05 | Finished product presentation acceptable | Yes | Yes | Yes | 50
ED-CLEAN | ED-CLEAN-01 | Production surfaces cleaned | Yes | No | Yes | 10
ED-CLEAN | ED-CLEAN-02 | Sinks / tools sanitized | Yes | No | Yes | 20
ED-CLEAN | ED-CLEAN-03 | Floors / visible areas clean | Yes | No | Yes | 30
ED-CLEAN | ED-CLEAN-04 | Trash removed | Yes | No | Yes | 40
ED-CLEAN | ED-CLEAN-05 | Restroom / customer area checked | Yes | No | Yes | 50
ED-INV | ED-INV-01 | Fruit shortages identified | Yes | No | Yes | 10
ED-INV | ED-INV-02 | Packaging shortages identified | Yes | No | Yes | 20
ED-INV | ED-INV-03 | Chocolate / ingredient shortages identified | Yes | No | Yes | 30
ED-INV | ED-INV-04 | Supply purchase request submitted if needed | No | No | No | 40
ED-CUST | ED-CUST-01 | Open customer complaints reviewed | Yes | Yes | Yes | 10
ED-CUST | ED-CUST-02 | Refunds / credits / voids reviewed | Yes | Yes | Yes | 20
ED-CUST | ED-CUST-03 | Recovery actions assigned | Yes | Yes | Yes | 30
ED-CUST | ED-CUST-04 | Negative reviews / guest connects checked | Yes | Yes | Yes | 40
ED-CLOSE | ED-CLOSE-01 | All same-day orders completed / accounted for | Yes | Yes | Yes | 10
ED-CLOSE | ED-CLOSE-02 | Tomorrow priority orders reviewed | Yes | No | Yes | 20
ED-CLOSE | ED-CLOSE-03 | Production area cleaned / sanitized | Yes | Yes | Yes | 30
ED-CLOSE | ED-CLOSE-04 | Waste / spoilage recorded | Yes | Yes | Yes | 40
ED-CLOSE | ED-CLOSE-05 | Refund / complaint issues recorded | Yes | Yes | Yes | 50
ED-CLOSE | ED-CLOSE-06 | Cash / POS close completed if applicable | Yes | Yes | Yes | 60
ED-CLOSE | ED-CLOSE-07 | Store secured / close complete | Yes | No | Yes | 70
ED-WEEK | ED-WEEK-01 | Week number and comparable LY week verified | Yes | Yes | Yes | 10
ED-WEEK | ED-WEEK-02 | Sales / orders / avg ticket actuals entered | Yes | Yes | Yes | 20
ED-WEEK | ED-WEEK-03 | Labor / COGS / refund metrics entered | Yes | Yes | Yes | 30
ED-WEEK | ED-WEEK-04 | Targets / variance / YoY reviewed | Yes | Yes | Yes | 40
ED-WEEK | ED-WEEK-05 | Customers this week reviewed | Yes | Yes | Yes | 50
ED-WEEK | ED-WEEK-06 | Top customer / recipient opportunities reviewed | Yes | Yes | Yes | 60
ED-WEEK | ED-WEEK-07 | Reviews / complaints / recoveries reviewed | Yes | Yes | Yes | 70
ED-WEEK | ED-WEEK-08 | Critical Moves reviewed / reset | Yes | Yes | Yes | 80
ED-WEEK | ED-WEEK-09 | Exceptions assigned | Yes | Yes | Yes | 90
ED-WEEK | ED-WEEK-10 | Next week targets and moves confirmed | Yes | Yes | Yes | 100
FI-WEEK | FI-WEEK-01 | Books current through required date | Yes | Yes | Yes | 10
FI-WEEK | FI-WEEK-02 | Bank / card reconciliation status reviewed | Yes | Yes | Yes | 20
FI-WEEK | FI-WEEK-03 | AP / AR reviewed | Yes | Yes | Yes | 30
FI-WEEK | FI-WEEK-04 | Cash position updated | Yes | Yes | Yes | 40
FI-WEEK | FI-WEEK-05 | Open creditor / legacy issues reviewed | Yes | Yes | Yes | 50
FI-WEEK | FI-WEEK-06 | Required finance evidence linked | Yes | Yes | Yes | 60
FI-WEEK | FI-WEEK-07 | Exceptions / next actions assigned | Yes | Yes | Yes | 70
HQ-WEEK | HQ-WEEK-01 | Critical Moves results reviewed | Yes | Yes | Yes | 10
HQ-WEEK | HQ-WEEK-02 | All required weekly checklists reviewed | Yes | Yes | Yes | 20
HQ-WEEK | HQ-WEEK-03 | Required operating-system closes / management results reviewed | Yes | Yes | Yes | 30
HQ-WEEK | HQ-WEEK-04 | Budget / forecast variance reviewed | Yes | Yes | Yes | 40
HQ-WEEK | HQ-WEEK-05 | Exceptions reviewed and owned | Yes | Yes | Yes | 50
HQ-WEEK | HQ-WEEK-06 | Waiting / blocked items reviewed | Yes | Yes | Yes | 60
HQ-WEEK | HQ-WEEK-07 | Decisions captured | Yes | Yes | Yes | 70
HQ-WEEK | HQ-WEEK-08 | Evidence gaps identified | Yes | Yes | Yes | 80
HQ-WEEK | HQ-WEEK-09 | Next week plan created | Yes | Yes | Yes | 90
HQ-WEEK | HQ-WEEK-10 | Owners / due dates confirmed | Yes | Yes | Yes | 100
HQ-MONTH | HQ-MONTH-01 | Financial month close complete | Yes | Yes | Yes | 10
HQ-MONTH | HQ-MONTH-02 | Finance month close confirmed from authoritative finance operating system | Yes | Yes | Yes | 20
HQ-MONTH | HQ-MONTH-03 | Monthly YoY reviewed | Yes | Yes | Yes | 30
HQ-MONTH | HQ-MONTH-04 | YTD vs LY and YTD target reviewed | Yes | Yes | Yes | 40
HQ-MONTH | HQ-MONTH-05 | Budget vs actual reviewed | Yes | Yes | Yes | 50
HQ-MONTH | HQ-MONTH-06 | Forecast updated | Yes | Yes | Yes | 60
HQ-MONTH | HQ-MONTH-07 | Customer / reputation review complete | Yes | Yes | Yes | 70
HQ-MONTH | HQ-MONTH-08 | People / capacity review complete | Yes | Yes | Yes | 80
HQ-MONTH | HQ-MONTH-09 | Recurring exceptions reviewed | Yes | Yes | Yes | 90
HQ-MONTH | HQ-MONTH-10 | Major decisions captured | Yes | Yes | Yes | 100
HQ-MONTH | HQ-MONTH-11 | Next month priorities / targets set | Yes | Yes | Yes | 110
HQ-MONTH | HQ-MONTH-12 | Month evidence / history retained | Yes | Yes | Yes | 120
GF-WEEK | GF-WEEK-01 | Product / quality status reviewed | Yes | Yes | Yes | 10
GF-WEEK | GF-WEEK-02 | Costing / margin current | Yes | Yes | Yes | 20
GF-WEEK | GF-WEEK-03 | Prospects / contacts / tastings entered | Yes | Yes | Yes | 30
GF-WEEK | GF-WEEK-04 | Standing accounts updated | Yes | Yes | Yes | 40
GF-WEEK | GF-WEEK-05 | Revenue / target / forecast reviewed | Yes | Yes | Yes | 50
GF-WEEK | GF-WEEK-06 | Budget / money required reviewed | Yes | Yes | Yes | 60
GF-WEEK | GF-WEEK-07 | Next moves assigned | Yes | Yes | Yes | 70
LC-WEEK | LC-WEEK-01 | Open obligations reviewed | Yes | Yes | Yes | 10
LC-WEEK | LC-WEEK-02 | Exposure values updated where known | Yes | Yes | Yes | 20
LC-WEEK | LC-WEEK-03 | Sellable offer / customer-facing quality constraint reviewed | Yes | Yes | Yes | 30
LC-WEEK | LC-WEEK-04 | Decision-useful price / cost / margin or constraint current | Yes | Yes | Yes | 40
LC-WEEK | LC-WEEK-05 | Closure evidence preserved | Yes | Yes | Yes | 50
LC-WEEK | LC-WEEK-06 | Closed items marked closed | Yes | Yes | Yes | 60

## HQ_CHECKLIST_RUNS
Run ID | Checklist ID | Business | Area | Checklist Name | Period Key | Period Type | Scheduled Date | Owner | Status | Required Items | Completed Items | Completion % | On Time? | Exceptions | Evidence Complete? | Started At | Completed At | Last Update
ED-OPEN-2026-08-30 | ED-OPEN | Edible | Store | Opening Checklist | 2026-08-30 | DAILY | 2026-08-30 | Store Lead | Not Started | 8 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-PROD-2026-08-30 | ED-PROD | Edible | Store | Production Readiness | 2026-08-30 | DAILY | 2026-08-30 | Store Lead | Not Started | 6 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-QA-2026-08-30 | ED-QA | Edible | Store | Food Safety / Quality | 2026-08-30 | DAILY | 2026-08-30 | Store Lead | Not Started | 5 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-CLEAN-2026-08-30 | ED-CLEAN | Edible | Store | Cleaning / Sanitation | 2026-08-30 | DAILY | 2026-08-30 | Store Team | Not Started | 5 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-INV-2026-08-30 | ED-INV | Edible | Store | Inventory / Supplies | 2026-08-30 | DAILY | 2026-08-30 | Store Lead | Not Started | 3 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-CUST-2026-08-30 | ED-CUST | Edible | Store | Customer Issues / Guest Connect | 2026-08-30 | DAILY | 2026-08-30 | Store Lead | Not Started | 4 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-CLOSE-2026-08-30 | ED-CLOSE | Edible | Store | Closing Checklist | 2026-08-30 | DAILY | 2026-08-30 | Store Lead | Not Started | 7 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
ED-WEEK-2026-W35 | ED-WEEK | Edible | Management | Edible Weekly Management Review | 2026-W35 | WEEKLY | 2026-08-30 | Coordinator | Not Started | 10 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
FI-WEEK-2026-W35 | FI-WEEK | Finance & Office | Management | Finance Week Close | 2026-W35 | WEEKLY | 2026-08-30 | Finance | In Progress | 7 | 2 | 29 |  | 0 | No |  |  | 2026-08-30 23:18
HQ-WEEK-2026-W35 | HQ-WEEK | Shared Management | Management | HQ Week Close | 2026-W35 | WEEKLY | 2026-08-30 | Coordinator | Not Started | 10 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
HQ-MONTH-2026-M08 | HQ-MONTH | Shared Management | Management | HQ Month Close | 2026-M08 | MONTHLY | 2026-08-30 | Coordinator | Not Started | 12 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
GF-WEEK-2026-W35 | GF-WEEK | Gardenia's Fire | Management | Gardenia Weekly Review | 2026-W35 | WEEKLY | 2026-08-30 | Coordinator | Not Started | 7 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14
LC-WEEK-2026-W35 | LC-WEEK | Legacy Closeout | Management | Legacy Closeout Weekly Review | 2026-W35 | WEEKLY | 2026-08-30 | Coordinator | Not Started | 6 | 0 | 0 |  | 0 | No |  |  | 2026-08-30 08:14

## HQ_TARGETS
Year | Week | Month | Business | Metric | Last Year | Target | Actual | Variance | Variance % | YoY % | Forecast | 4W Trend | YTD Actual | YTD Last Year | YTD Target | Next Move | Owner | Source

## HQ_BUDGETS
Year | Month | Business | Revenue Budget | Gross Profit Budget | Net Profit Budget | Labor Budget | COGS Budget | Marketing Budget | Other Budget | Money Required | Expected Return | Forecast Revenue | Forecast Net Profit | Owner | Notes

## HQ_CUSTOMERS
Date | Week | Year | Business | Customer | Type | Revenue | Orders | New / Repeat | Recipient? | Recipient Name | Recipient Contactable? | Business Opportunity? | Top Customer? | Relationship Stage | Last Order | Next Action | Owner | Due | Source / Evidence

## HQ_REVIEWS
Date | Week | Business | Platform | Rating | Review / Issue | Theme | Severity | Response Status | Recovery | Owner | Next Action | Source / Evidence

## HQ_DECISIONS
Decision ID | Date | Business / Area | Decision | Why | Owner | Due | Status | Result / Follow-up | Evidence

## HQ_EXCEPTIONS
Exception ID | Date | Business / Area | Source Type | Source ID | Exception | Severity | Financial Exposure | Owner | Status | Next Action | Due | Age Days | Recurring? | Evidence | Closed Date

## HQ_NOTES
Timestamp | Business / Area | Source Type | Source ID | Note | Author
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 22:47 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-30 23:17 |  | Checklist Item | FI-WEEK-2026-W35¦FI-WEEK-01 | {"status":"PASS","note":"","evidence":"","updated":"2026-08-31T03:17:21.771Z","user":"ahmad@wolfventuresnj.com"} | ahmad@wolfventuresnj.com
2026-08-30 23:17 |  | Checklist Item | FI-WEEK-2026-W35¦FI-WEEK-01 | {"status":"PASS","note":"","evidence":"","updated":"2026-08-31T03:17:22.758Z","user":"ahmad@wolfventuresnj.com"} | ahmad@wolfventuresnj.com
2026-08-30 23:17 |  | Checklist Item | FI-WEEK-2026-W35¦FI-WEEK-02 | {"status":"PASS","note":"","evidence":"","updated":"2026-08-31T03:17:22.928Z","user":"ahmad@wolfventuresnj.com"} | ahmad@wolfventuresnj.com
2026-08-31 01:35 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-08-31 01:35 | Gardenia's fire | IDEA | CAPTURE | Mini Fruit cups | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com
2026-09-01 12:56 | My Work | IDEA | CAPTURE |  | ahmad@wolfventuresnj.com

## HQ_ALERTS
Alert ID | Created | Business / Area | Type | Message | Severity | Owner | Status | Source Type | Source ID | Due | Resolved At
AL-de5dcc2c | 2026-08-30 08:14 | Edible | Incomplete Control | Edible Weekly Management Review is 0% complete | Medium | Coordinator | Open | Checklist Run | ED-WEEK-2026-W35
AL-e65b0945 | 2026-08-30 08:14 | Finance & Office | Incomplete Control | Finance Week Close is 0% complete | Medium | Finance | Open | Checklist Run | FI-WEEK-2026-W35
AL-aaadb52d | 2026-08-30 08:14 | Shared Management | Incomplete Control | HQ Week Close is 0% complete | Medium | Coordinator | Open | Checklist Run | HQ-WEEK-2026-W35
AL-6f1253c8 | 2026-08-30 08:14 | Shared Management | Incomplete Control | HQ Month Close is 0% complete | Medium | Coordinator | Open | Checklist Run | HQ-MONTH-2026-M08
AL-ced04ef5 | 2026-08-30 08:14 | Gardenia's Fire | Incomplete Control | Gardenia Weekly Review is 0% complete | Medium | Coordinator | Open | Checklist Run | GF-WEEK-2026-W35
AL-b0fe3756 | 2026-08-30 08:14 | Legacy Closeout | Incomplete Control | Legacy Closeout Weekly Review is 0% complete | Medium | Coordinator | Open | Checklist Run | LC-WEEK-2026-W35
AL-6f36b4ca | 2026-08-30 08:14 | Edible Operations | Work Exception | Execute labor schedule correction and verify effect needs attention | High | Emmanuel | Open | Work | W-004
AL-7f7f4074 | 2026-08-30 08:14 | Finance & Office | Work Exception | Confirm books/reconciliations/evidence current for weekly close needs attention | High | Moises | Open | Work | W-005
AL-92c3ae02 | 2026-08-30 08:14 | Finance & Office | Work Exception | Review open creditors / obligations with Emmanuel needs attention | High | Moises | Open | Work | W-006
AL-e7327654 | 2026-08-30 08:14 | Ahmad Personal Finance / Life | Work Exception | Establish lightweight personal bills / obligations source map and weekly control needs attention | High | Moises | Open | Work | W-008

## HQ_ACTIVITY
Timestamp | User | Action Type | Business / Area | Source Type | Source ID | Old Value | New Value | Detail
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 22:47 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-30 23:17 | ahmad@wolfventuresnj.com | CHECKLIST ITEM UPDATE |  | Checklist Item | FI-WEEK-2026-W35¦FI-WEEK-02 |  | PASS
2026-08-30 23:18 | ahmad@wolfventuresnj.com | CHECKLIST ITEM UPDATE |  | Checklist Item | FI-WEEK-2026-W35¦FI-WEEK-01 |  | PASS
2026-08-30 23:18 | ahmad@wolfventuresnj.com | CHECKLIST ITEM UPDATE |  | Checklist Item | FI-WEEK-2026-W35¦FI-WEEK-01 |  | PASS
2026-08-31 01:35 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-08-31 01:35 | ahmad@wolfventuresnj.com | NOTE ADDED | Gardenia's fire | IDEA | CAPTURE |  | Mini Fruit cups
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:56 | ahmad@wolfventuresnj.com | NOTE ADDED | My Work | IDEA | CAPTURE
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-011 |  | Open
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-012 |  | Open
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-013 |  | Open
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-014 |  | Open | xfgnxfm
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-016 |  | Open | xfgnxfm
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-015 |  | Open | xfgnxfm
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-016 |  | Open | xfgnxfm
2026-09-01 12:58 | ahmad@wolfventuresnj.com | WORK CREATED | My Work | Work | W-017 |  | Open | xfgnxfm

## HQ_LEGACY_CLOSEOUT
Item ID | Old Company / Entity | Creditor / Issue | Amount / Exposure | Stage | Risk | Owner | Next Action | Due | Evidence / Drive Link | Last Update | Closed Date

## HQ_PROPERTY
Property | Category | Item | Status | Amount | Due / Renewal | Owner | Next Action | Source / Evidence | Notes

## HQ_READINESS
Area | System / Source | Status | Authoritative? | Owner | Drive / Source Link | Last Verified | Issue / Next Action
HQ Core | AHMAD HQ — PHASE 1 OPERATING CORE — Sep 2026 | BUILT / STATIC-QA / PARTIALLY POPULATED | Yes for management state; No for underlying transaction truth | Emmanuel / Ahmad | https://docs.google.com/spreadsheets/d/1_zaAT-zqEQhwTW2ZNRLSnH8Peed7zZTzi3kd0RUHQRQ/edit | 2026-09-01 | Harden defects, complete source/readiness wiring, and prove one real multi-user weekly cycle.
HQ Web App | Apps Script two-file deploy build release 1.4.9 | BUILT / DEFECTS / DEPLOYMENT VERSION TO VERIFY | N/A | Technical owner / developer | Drive code artifact 1iulushugXJAhrbP7z4WpMqyFCKo5zFTt | 2026-09-01 | Confirm exact deployed release; fix duplicate writes, #REF!, known UI defects; add locking/idempotency/error logging; regression test and rollback.
Source Governance | HQ_SOURCE_MAP | POPULATING — FIRST VERIFIED PASS COMPLETE | Yes as wiring registry | Emmanuel + source owners | AHMAD HQ Phase 1 Core — HQ_SOURCE_MAP | 2026-09-01 | Verify remaining transactional links, owners, calculations and automation paths before calling production-ready.
Finance & Office | OFFICE FINANCE — LIVE CONTROL SYSTEM — REVISED Aug 2026 | BUILT / STRUCTURE VERIFIED / LIVE USE EARLY | Yes for finance-control status; underlying QuickBooks/banks remain transaction truth | Moises → Emmanuel | https://docs.google.com/spreadsheets/d/1zrY3SOQiF2g8A_7z4ynA9mVnM7_qsvS8eBsebBRplmc/edit | 2026-09-01 | Weekly Review and Phase 1 Verification are mostly NOT STARTED; complete first evidenced close and reconcile source links.
Edible | Edible Hackensack — Store Operations Control System — v3 — Aug 2026 | BUILT / STRUCTURE VERIFIED / ADOPTION EARLY | Yes for operational control; POS/franchise/payroll/accounting are underlying source truth | Store Lead → Emmanuel | https://docs.google.com/spreadsheets/d/1_qBjYd0F4BYYTxLMJjEZbQynBdHH5JGe83-U7nheJOE/edit | 2026-09-01 | Run a complete real Week Close with actual KPIs/evidence; verify no duplicate reporting between Edible and HQ.
Gardenia CRM | HighLevel | PLANNED / NOT WIRED | Planned authoritative relationship/pipeline source | Emmanuel / revenue owner | Not yet verified in HQ | 2026-09-01 | Configure relationship model/pipeline only after launch fields are locked; start simplest integration/export path.
Gardenia Commerce | Shopify | PLANNED / NOT READY | Planned authoritative order/customer commerce source | Emmanuel + Moises | Not yet verified in HQ | 2026-09-01 | Do not custom-build commerce in HQ; configure Shopify and feed management roll-ups when orders begin.
Ironmark | HighLevel + lightweight operating/job records | MODEL VERIFIED / LIVE SYSTEM NOT READY | Planned | Emmanuel / assigned revenue owner | Current model: https://docs.google.com/document/d/1IiSyQbFeaLvEEm2PaktBr5HxhgnDWDN6D9rwvznXZoU/edit | 2026-09-01 | Activate pilot source: lane, providers, leads, completed jobs, economics and QA before adding specialized field-service software.
Permissions | HQ_ACCESS + Apps Script access-control functions | BUILT / NOT LIVE-VERIFIED | Yes for HQ permission policy | Technical owner + Emmanuel | AHMAD HQ Phase 1 Core + deployed web app | 2026-09-01 | Production blocker until role-by-role view/create/edit/close/admin and sensitive-data tests pass.
Reliability | Write/concurrency/error-handling layer | NOT PRODUCTION-HARDENED | N/A | Senior Apps Script engineer | Apps Script deploy code | 2026-09-01 | No LockService found; add locking, idempotency, duplicate-submit protection, centralized error logging and regression tests.
Operating Acceptance | Real multi-user weekly cycle | NOT PROVEN | N/A | Emmanuel + Moises + operating users | HQ + Finance + Edible live systems | 2026-09-01 | Run plan → execute → evidence → exception → review → next plan; measure duplicate entry, chasing, close time, self-management and user friction.
Drive / Institutional Memory | AHMAD — WORKSPACE 2026 + current source documents | AVAILABLE / CANONICAL CLEANUP STILL NEEDED | Yes for durable documents/evidence when current location is verified | Emmanuel + AI | Google Drive workspace | 2026-09-01 | Continue CURRENT / REFERENCE / SUPERSEDED / DUPLICATE / UNCLEAR reconciliation without deleting history.
Test / Production Separation | HQ checklist/test activity versus authoritative operating controls | NOT ADEQUATELY SEPARATED | No — test activity must never be treated as operating truth | Technical owner + Emmanuel | HQ_CHECKLIST_RUNS/HQ_NOTES + underlying operating systems | 2026-09-01 | Finance HQ run shows 2/7 from UI/test clicks while Finance Weekly Review remains NOT STARTED. Add staging/test-data discipline or explicit Test/Live flag, evidence/source validation, and clean/reset procedure before production.
Final HQ Acceptance Gate | Patty + Ahmad code / live acceptance review | NOT READY — HARDENING GATES OPEN | N/A | Patty / Ahmad + technical owner + AI QA | AI Working Ledger — HQ GAP & INTEGRITY | 2026-09-03 | Pass/fail gates: exact release identity; unique-ID/write integrity; test/live separation; permissions; critical UI defects; error logging/rollback/concurrency; one complete live management cycle; demonstrated reduction in duplicate reporting/chasing; then staged cutover.
Gardenia Operating Boundary | Real-life product process → HQ management roll-up | BOUNDARY CORRECTED — NO HQ PRODUCT-DEVELOPMENT WORKSTREAM | Real-life operating process authoritative for product development/testing; HQ authoritative only for management state | Emmanuel → Emmanuel/HQ | Gardenia operating process + HQ Gardenia/Work Desk | 2026-09-03 | Do not require separate SKU/product-development tracker or product-development acceptance gate. Capture sellable readiness, decision-useful price/cost/margin, capacity/constraints, market activity, orders/repeat, exceptions and owner decisions.
Duplicate Operating Controls | Edible v3 + Office Finance controls versus HQ checklist engine | CONFIGURATION CORRECTED — PARALLEL CHECKLIST GENERATION DISABLED | Edible v3 remains operating truth for daily/store Week Close; Office Finance Weekly Review remains operating truth for finance close. HQ remains management roll-up/review layer. | Store/finance staff should not perform same control twice. | Edible daily ED-* and ED-WEEK plus FI-WEEK checklist definitions set Active? = No. Existing historical/test runs are preserved for QA/history; do not treat them as live operating truth. | 2026-09-03 | Next technical acceptance: prove HQ can consume/reflect result + exception state without manual re-keying.
People operating boundary | Authoritative schedule/HR/payroll sources → HQ management capacity roll-up | BOUNDARY CORRECTED — HQ NOT HR/SCHEDULING SYSTEM | Source systems own detailed schedule/HR truth; HQ owns only decision-useful management state | Emmanuel / functional owner | PEOPLE & CAPACITY + HQ_ACCESS | 2026-09-03 | Keep role ownership, capacity/conflict, coverage/backup and material availability changes. Do not build duplicate detailed roster, timesheet, payroll or scheduling maintenance in HQ.
Finance register boundary | HQ_FINANCE_REGISTER | REFERENCE / EXPOSURE INDEX — NOT CURRENT BALANCE LEDGER | No; current balances and transaction truth remain banks/cards/lenders/QuickBooks and source evidence | Moises → Emmanuel/HQ | HQ_FINANCE_REGISTER + authoritative finance sources | 2026-09-03 | Preserve stale/historical exposure rows as reference. Do not maintain parallel current balances in HQ. HQ should show material obligation/exposure, current-through/source status, exception, owner, deadline and decision need only.
System Access / Training boundary | HQ_SYSTEM_ACCESS + HQ_TRAINING | SCHEMA ONLY / POPULATE BY EXCEPTION | No for credentials/full training records; yes only for management control state | Emmanuel / system owner | Actual systems, Drive guides, provider/admin records | 2026-09-03 | Do not turn HQ into password vault, LMS, or duplicate access directory. Track only consequential access ownership, missing/disabled access, required capability gap, training exception, backup coverage or control issue.

## HQ_PERIODS
Period Key | Period Type | Year | Week | Month | Start Date | End Date | Status | Completion % | Result Review Complete? | Decision Review Complete? | Next Period Plan Complete? | Closed At | Closed By

## MONTH PLAN
SEPTEMBER 2026 — MONTH PLAN
THIS MONTH MUST PRODUCE
1. Launch Gardenia's offer and create real local sales activity. 2. Bring Edible labor and sales performance under tighter weekly control. 3. Get Finance / Office weekly close reliable and evidenced. 4. Operate the HQ system through real work, not separate reporting. 5. Protect Ahmad's time for income-producing and high-value work. | [6 empty] | SUN | MON | TUE | WED | THU | FRI | SAT
[7 empty] | 30 | 31 | 1 | 2 | 3 | 4 | 5
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12
[7 empty] | 13 | 14 | 15 | 16 | 17 | 18 | 19
[7 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26
[7 empty] | 27 | 28 | 29 | 30 | 1 | 2 | 3
MONTHLY ACTION PLAN — PURPOSE → RESULT → WEEKLY MOVES
FUNCTION / PROJECT | FOCUS | MONTHLY OUTCOME | HOW WE'LL KNOW | OWNER | WEEK 1 MOVE | WEEK 2 | WEEK 3 | WEEK 4 | MONTH-END RESULT / LEARNING
Edible Operations | MAINTAIN | Stabilize store performance while improving labor productivity and sales discipline. | Sales trend; labor %; customer/service exceptions; Week Close reliability. | Emmanuel / Store | Labor correction + marketing execution
Gardenia's Fire | PUSH | Move from preparation into actual local sales activity and first standing accounts. | Prospects; calls; tastings; standing accounts; weekly revenue. | Emmanuel | Product/cost + target list + outreach
Finance & Office | PUSH | Create reliable weekly financial visibility with evidence and no silent material issues. | Books current; reconciliations; A/P/A/R reviewed; evidence complete; exceptions assigned. | Moises → Emmanuel | Complete first clean weekly close
Podcast / Legacy | PUSH | Keep production moving from script/recording through review/edit/retain. | Recordings reviewed; edits moved; useful material retained. | Ahmad + Emmanuel | Move current video/editor to next executable step
People / Systems | MAINTAIN | Make roles, schedules, priorities and follow-through visible without duplicate reporting. | Owners clear; Viane placement resolved; weekly rhythm actually used. | Emmanuel | Run system from real work; confirm capacity
Ahmad Personal Finance / Life | PUSH | Gain compressed visibility of personal obligations, recurring charges and decisions without another bureaucracy. | Bills/obligations visible; recurring charges reviewed; exceptions escalated. | Moises / Emmanuel / Ahmad | Establish source map + weekly review
MONTH CLOSE — DID THE MONTH ACTUALLY MOVE THE BUSINESS?
DONE? | CLOSE QUESTION | OWNER | RESULT / EXCEPTION / LEARNING
FALSE | Were the month's most important outcomes materially advanced or closed? | Emmanuel / Ahmad
FALSE | Did Edible's sales/labor/customer picture improve, deteriorate or stay flat — and why? | Emmanuel
FALSE | Did Gardenia's produce real market activity and conversion learning? | Emmanuel
FALSE | Is Finance / Office more current, evidenced and exception-driven than at month start? | Moises / Emmanuel
FALSE | Did this operating system reduce memory dependence and duplicate reporting? | Emmanuel / Ahmad
FALSE | What should be PUSH / MAINTAIN / PARK next month? | Ahmad

## THIS WEEK
THIS WEEK — EXECUTION BOARD
Week of Aug 31–Sep 4 • Finish meaningful outcomes, not administrative theater
OPEN CRITICAL MOVES 6 |  |  | RESULT-PRODUCING 10 |  |  | WAITING / BLOCKED 0 |  |  | AHMAD DECISIONS 1
WEEKLY OUTCOMES / CRITICAL MOVES
PROJECT / FUNCTION | NEXT ACTION | OWNER | FOCUS | DUE | STATUS | WAITING ON | ESCALATE?
Gardenia's Fire | Confirm sellable offer is ready from Emmanuel's real-life process; capture only price/cost/margin or constraints needed for selling/management | Emmanuel | PUSH | 2026-08-31 | In Progress |  | No
Gardenia's Fire | Build/confirm target account list | Emmanuel | PUSH | 2026-09-01 | Open |  | No
Gardenia's Fire | Begin outreach and schedule tastings | Emmanuel | PUSH | 2026-09-04 | Open |  | No
Edible Operations | Execute labor schedule correction and verify effect | Emmanuel | MAINTAIN | 2026-09-02 | In Progress |  | Yes
Finance & Office | Confirm books/reconciliations/evidence current for weekly close | Moises | PUSH | 2026-09-04 | Open |  | Yes
My Work | xfgnxfm | xfmfhm | PUSH | xmh | Open |  | No
RECURRING CONTROLS / WEEK CLOSE
FUNCTION | CONTROL | OWNER | DUE | STATUS | EXCEPTION?
#REF!
WEEK MAP — PUT THE WORK INTO THE WEEK, NOT JUST ON A LIST
MON • AUG 31 |  | TUE • SEP 1 |  | WED • SEP 2 |  | THU • SEP 3 |  | FRI • SEP 4
Emmanuel — Confirm sellable offer is ready from Emmanuel's real-life process; capture only price/cost/margin or constraints needed for selling/management Emmanuel — Operate Monday launch from HQ role views; confirm owners, dates, blockers and exceptions are current |  | Emmanuel — Build/confirm target account list Emmanuel — Move current video/editor follow-up to next executable step |  | Emmanuel — Execute labor schedule correction and verify effect Emmanuel — Review subscriptions / recurring charges and surface cancellations or decisions needed |  | Moises — Review open creditors / obligations with Emmanuel |  | Emmanuel — Begin outreach and schedule tastings Moises — Confirm books/reconciliations/evidence current for weekly close Moises — Establish lightweight personal bills / obligations source map and weekly control

## RESULTS & EXCEPTIONS
RESULTS & EXCEPTIONS
Targets → actuals → exceptions → next action. Management sees movement, not reporting theater.
EDIBLE SALES $7,547 / $9,300 |  |  | EDIBLE LABOR 35.5% / 22.0% |  |  | GARDENIA'S ACCOUNTS NOT REPORTED | FINANCE CONTROLS OPEN 4
KPI SCOREBOARD
PROJECT / FUNCTION | METRIC | TARGET | ACTUAL | TREND | MEANING / EXCEPTION | OWNER
Edible Operations | Net Sales | $9,300 | $7,547 | Down | Below target | Emmanuel
Edible Operations | Labor % | 22.0% | 35.5% | Up / Bad | Materially above target | Emmanuel
Edible Operations | Refund + Void % |  | 3.7% |  | Elevated | Emmanuel
Gardenia's Fire | Prospects Identified |  |  |  |  | Emmanuel
Gardenia's Fire | Contacts Made |  |  |  |  | Emmanuel
Gardenia's Fire | Tastings |  |  |  |  | Emmanuel
Gardenia's Fire | Standing Accounts |  |  |  |  | Emmanuel
Gardenia's Fire | Weekly Revenue |  |  |  |  | Emmanuel
WORK EXCEPTIONS / MANAGEMENT ESCALATIONS
PROJECT / FUNCTION | NEXT ACTION | OWNER | DUE | STATUS | WAITING ON
Edible Operations | Execute labor schedule correction and verify effect | Emmanuel | 2026-09-02 | In Progress
Finance & Office | Confirm books/reconciliations/evidence current for weekly close | Moises | 2026-09-04 | Open
Finance & Office | Review open creditors / obligations with Emmanuel | Moises | 2026-09-03 | Open | Emmanuel
CONTROL EXCEPTIONS
FUNCTION | CONTROL | OWNER | DUE | STATUS | NOTES / NEXT ACTION
No control exceptions

## EDIBLE — OPERATE
EDIBLE HACKENSACK — OPERATE
NET SALES\n$7,547 / $9,300 |  |  | LABOR\n35.5% / 22.0% |  |  | REFUND + VOID\n3.7% |  |  | CURRENT MANAGEMENT EXCEPTION Sales below target and labor materially above target. Current question: did the schedule/labor correction actually change the result?
STORE PEOPLE & COVERAGE — MANAGEMENT VIEW
PERSON | ROLE | MON | TUE | WED | THU | FRI | SAT | COVERAGE / RESPONSIBILITY | EXCEPTION / NEED
Cathy | Store Lead | — | Working | — | Working | Working | Working | Store lead coverage; ~30–32 hrs/week current known pattern | Verify current week schedule
Lorena | Production | TBD | TBD | TBD | TBD | TBD | TBD | Production continuity / quality | Confirm current schedule
STORE WEEK CLOSE — ROLL-UP, NOT A SECOND CHECKLIST
CONTROL AREA | WHAT MANAGEMENT NEEDS TO KNOW | STATUS | EXCEPTION / NEXT ACTION
Staffing / schedule | Coverage adequate? labor aligned to sales? | Review
Production / delivery | Quality, workload, delivery issues? | Review
Inventory / waste / purchasing | Shortage, bad fruit, waste, ordering exceptions? | Review
Customer / service | Complaints, refunds, recovery, repeat issue? | Review
Sales / marketing | Lead behaviors performed? did they move sales? | Review
Cash / bookkeeping | Deposit or bookkeeping exception requiring attention? | Review
CURRENT MOVES — JUDGE THEM AGAINST THE NUMBERS
Execute labor schedule correction and verify effect | Emmanuel | 2026-09-02 | In Progress
OPEN DETAILED EDIBLE SYSTEM\nSupervisor Daily • Weekly Control • Week Close • KPIs • Customers • Standards • Month Close

## GARDENIA — OPERATE
GARDENIA'S FIRE — OPERATE
PROSPECTS\n |  |  | CONTACTS\n |  |  | TASTINGS / ACCOUNTS\n / |  |  | THIS MONTH'S TEST Can Emmanuel's real-life product process produce an offer that local companies will taste, buy and repeat? HQ judges market activity, conversion, economics and exceptions — not product-development preparation.
CURRENT CRITICAL MOVES
Confirm sellable offer is ready from Emmanuel's real-life process; capture only price/cost/margin or constraints needed for selling/management | Emmanuel | 2026-08-31 | In Progress
Build/confirm target account list | Emmanuel | 2026-09-01 | Open
Begin outreach and schedule tastings | Emmanuel | 2026-09-04 | Open
1 Sellable offer confirmed by Emmanuel
1 Product / costing ready | → | 2 Target company identified | → | 3 Contact made | → | 4 Tasting / sample | → | 5 Follow-up / close | → | 6 Standing account | → | 7 Weekly revenue
OPEN CALLS & FOLLOW-UP\nWork prospects and next touches here |  |  |  |  | OPEN GARDENIA'S PROJECT HOME\nProducts • pricing • target lists • source files

## CALLS & FOLLOW-UP
CALLS & FOLLOW-UP — WORK DESK
Use for Gardenia's prospects, creditors/vendor calls, office follow-ups, customer recovery or any meaningful follow-up. Filter by owner, stage or date.
COMPANY / PERSON | FUNCTION / PROJECT | CONTACT | WHY / PURPOSE | STAGE | LAST CONTACT | NEXT FOLLOW-UP | OWNER | STATUS | RESULT / WHAT HAPPENED | NEXT MOVE | DAYS SINCE TOUCH | SOURCE / NOTES | LAST UPDATED
Sample — replace | Gardenia's Fire |  | Introduce offer / schedule tasting | Target |  |  | Emmanuel | Open |  | Make first contact
Formulas:
DAYS SINCE TOUCH = IF([LAST CONTACT]="","",TODAY()-[LAST CONTACT])

## PEOPLE & CAPACITY
PEOPLE, SCHEDULE & CAPACITY
WEEKLY CAPACITY BOARD — CURRENT KNOWN SCHEDULE / CONFIRMATIONS
PERSON | FUNCTION | MON | TUE | WED | THU | FRI | SAT | SUN | THIS WEEK'S PRIORITY | CAPACITY / CONFLICT | STATUS
Ahmad | Decisions / high-value work | Decisions | Decisions | Protect | Protect | Review | Protect | Management | Income-producing/high-value + decisions | Do not fill with system-maintenance work | Active
Emmanuel | Coordinator / Integrator | Confirm | Confirm | Confirm | Confirm | Confirm | — | Review | Gardenia's + Edible + integration | Multiple interim roles; avoid bookkeeping burden | Confirm
Moises | Finance / Bookkeeping | 11–5 | 11–4 | 11–4 | 11–4 | 11–5 | — | As needed | Books / reconciliations / creditors / evidence | Use finance mechanism; escalate exceptions | Active
Viane | Role / placement to confirm | Confirm | Confirm | Confirm | Confirm | Confirm | Confirm | — | Confirm role + one contained responsibility | Do not broaden until ownership/result clear | Confirm
Cathy | Edible Store Lead | — | Working | — | Working | Working | Working | — | Store coverage + labor/service control | Verify weekly schedule vs sales/labor demand | Active
Lorena | Edible Production | TBD | TBD | TBD | TBD | TBD | TBD | — | Production continuity / quality | Confirm current schedule | Active
WHO IS CARRYING WHAT — LIVE FROM WORK DESK
Ahmad | Owner / Final Accountability | Decisions / priorities; income-producing/high-value activity; podcast | Protect decision and high-value time |  |  | Active
Emmanuel | Coordinator / Integrator | Gardenia's; Edible correction; Finance integration; systems rollout | Current capacity to confirm | Multiple interim roles / avoid bookkeeping burden | Ahmad | Active
Moises | Finance / Bookkeeping | Books/reconciliations; creditors; evidence; Phase 1 back-end support | Standing schedule to confirm for this week |  | Emmanuel | Active
Viane | New Staff — Role to Confirm | Confirm role / availability; assign one contained responsibility with clear result | Confirm current schedule / capacity | Do not broaden until ownership and result are clear | Emmanuel | Confirm
Cathy | Edible Store Lead | Store coverage; labor discipline; service; week-close execution | Tue / Thu / Fri / Sat; ~30–32 hrs/wk current known pattern — verify weekly | Schedule should align with labor target and store demand | Emmanuel | Active
Lorena | Edible Production | Production continuity; quality; readiness | Current schedule to confirm | Confirm coverage and responsibilities | Cathy / Emmanuel | Active

## AHMAD — CONTROL
AHMAD — CONTROL
Only what requires ownership, judgment, money, risk or your attention should rise here.
OPEN DECISIONS 1 |  |  | WAITING ON AHMAD 1 |  |  | MATERIAL ESCALATIONS 3 | PERSONAL CONTROLS OPEN 3
DECISIONS / APPROVALS
PROJECT / FUNCTION | DECISION NEEDED | REQUESTED BY | NEEDED BY | STATUS | DIRECTION / DECISION
Gardenia's Fire | Confirm launch offer / pricing after product costing is complete | Emmanuel | 2026-09-01 | Open
People / Systems | Hire external Google Workspace / AppSheet integrator now? | Ahmad | 2026-08-30 | Decided | Not yet. Continue ChatGPT-led build; revisit only if hands-on AppSheet/configuration burden warrants temporary help.
PERSONAL LIFE / PERSONAL FINANCE — COMPRESSED CONTROL
CONTROL | OWNER | DUE | STATUS | EXCEPTION? | NOTES / NEXT ACTION
Upcoming personal bills/obligations reviewed | Moises | 2026-09-04 | Open | No
Money-in / money-out and material exceptions reviewed | Moises | 2026-09-04 | Open | No
Personal-finance exceptions / deadlines reviewed and escalated to Ahmad | Emmanuel | 2026-09-04 | Open | No | Coordinate completeness and decisions; do not duplicate bookkeeping
INCOME / HIGH-VALUE WORK — PROTECT THIS
PROJECT / FUNCTION | NEXT ACTION | OWNER | DUE | STATUS | WAITING ON
Gardenia's Fire
Gardenia's Fire | Build/confirm target account list | Emmanuel | 46266 | Open
Gardenia's Fire | Begin outreach and schedule tastings | Emmanuel | 2026-09-04 | Open
Edible Operations | Execute labor schedule correction and verify effect | Emmanuel | 2026-09-02 | In Progress
Ahmad Personal Finance / Life | Review subscriptions / recurring charges and surface cancellations or decisions needed | Emmanuel | 2026-09-02 | Open
My Work | xfgnxfm | xfmfhm | xmh | Open
My Work | xfgnxfm | xfmfhm | xmh | Open
My Work | xfgnxfm | xfmfhm | xmh | Open
My Work | xfgnxfm | xfmfhm | xmh | Open
My Work | xfgnxfm | xfmfhm | xmh | Open

## EMMANUEL — HOME
EMMANUEL — COORDINATOR / INTEGRATOR
Your job: move priorities through people and systems; surface exceptions; do not recreate reports that already exist.
MY OPEN WORK 7 |  |  |  | MY CRITICAL MOVES 4 |  |  |  | WAITING / BLOCKED 0
MY WEEK — OPEN WORK
PROJECT / FUNCTION | NEXT ACTION | PRIORITY | CRITICAL? | DUE | STATUS | WAITING ON | ESCALATE?
Gardenia's Fire | Confirm sellable offer is ready from Emmanuel's real-life process; capture only price/cost/margin or constraints needed for selling/management | PUSH | Yes | 46265 | In Progress |  | No
Gardenia's Fire | Build/confirm target account list | PUSH | Yes | 46266 | Open |  | No
Gardenia's Fire | Begin outreach and schedule tastings | PUSH | Yes | 46269 | Open |  | No
Edible Operations | Execute labor schedule correction and verify effect | MAINTAIN | Yes | 46267 | In Progress |  | Yes
Podcast / Legacy | Move current video/editor follow-up to next executable step | PUSH | HOLD / TEST DATA | 46266 | Open | Ahmad | No
Ahmad Personal Finance / Life | Review subscriptions / recurring charges and surface cancellations or decisions needed | TEST | HOLD / TEST DATA | 46267 | Open |  | No
People / Systems | Operate Monday launch from HQ role views; confirm owners, dates, blockers and exceptions are current | TEST | HOLD / TEST DATA | 46265 | Open |  | No
MY RECURRING CONTROLS / WEEK CLOSE
FUNCTION | CONTROL | CADENCE | STATUS | EXCEPTION?
Edible Operations | Week Close completed and exceptions identified | Weekly | Open | No
People / Systems | Critical Moves reviewed; overdue/blocked escalated | Weekly | Open | No
Ahmad Personal Finance / Life | Personal-finance exceptions / deadlines reviewed and escalated to Ahmad | Weekly | Open | No

## MOISES — HOME
MOISES — FINANCE / BACK-END CONTROL
Keep the back end current, evidenced and exception-driven. Detailed bookkeeping stays in the finance system; HQ receives the roll-up.
MY OPEN WORK 3 |  |  |  | FINANCE CONTROLS OPEN 6 |  | CONTROL EXCEPTIONS 0
FINANCE WEEK CLOSE — CONTROLS
CONTROL | CADENCE | NEXT DUE | STATUS | EXCEPTION? | NOTES / NEXT ACTION
Books current / posted through agreed close date | Weekly | 46269 | Open | No
Bank and credit-card reconciliations current | Weekly | 46269 | Open | No
Critical A/P and A/R reviewed | Weekly | 46269 | Open | No
Evidence / supporting documents confirmed | Weekly | 46269 | Open | No
Upcoming personal bills/obligations reviewed | Weekly | 46269 | Open | No
Money-in / money-out and material exceptions reviewed | Weekly | 46269 | Open | No
MY OTHER OPEN WORK
PROJECT / FUNCTION | NEXT ACTION | PRIORITY | DUE | STATUS | WAITING ON
Finance & Office | Confirm books/reconciliations/evidence current for weekly close | PUSH | 46269 | Open
Finance & Office | Review open creditors / obligations with Emmanuel | PUSH | 46268 | Open | Emmanuel
Ahmad Personal Finance / Life | Establish lightweight personal bills / obligations source map and weekly control | PUSH | 46269 | Open

## WORK DESK — UPDATE
WORK DESK — CAPTURE • PLAN • UPDATE • CLOSE
ID | Project / Function | Work Item / Next Action | Owner | Type | Priority | Critical Move? | Income / Result Producing? | Due Date | Status | Waiting On | Blocked? | Result / Completion Note | Evidence / Drive Link | Created / Captured | Last Update | Management Escalation? | PLANNED DAY | WHY / OUTCOME SUPPORTED | COMPLETED AT | AGE / STALE
W-001 | Gardenia's Fire | Confirm sellable offer is ready from Emmanuel's real-life process; capture only price/cost/margin or constraints needed for selling/management | Emmanuel | Operating Result | PUSH | Yes | Yes | 2026-08-31 | In Progress |  | No |  | https://drive.google.com/drive/folders/1-CWhZsNUR2dnbbCLLOInkSOOHtFU_utm | 2026-08-30 | 2026-08-30 | No | Mon Aug 31 | Sales readiness / management economics without duplicating product development |  | 4d
W-002 | Gardenia's Fire | Build/confirm target account list | Emmanuel | Project Action | PUSH | Yes | Yes | 2026-09-01 | Open |  | No |  | https://drive.google.com/drive/folders/1LvDMFZKtN8Os89nodgQhUsqinqHelkRm | 2026-08-30 | 2026-08-30 | No | Tue Sep 1 | Create qualified sales pipeline |  | 4d
W-003 | Gardenia's Fire | Begin outreach and schedule tastings | Emmanuel | Project Action | PUSH | Yes | Yes | 2026-09-04 | Open |  | No |  | https://drive.google.com/drive/folders/1LvDMFZKtN8Os89nodgQhUsqinqHelkRm | 2026-08-30 | 2026-08-30 | No | Wed–Fri | Create tastings / standing-account conversations |  | 4d
W-004 | Edible Operations | Execute labor schedule correction and verify effect | Emmanuel | Improvement | MAINTAIN | Yes | Yes | 2026-09-02 | In Progress |  | No |  | https://docs.google.com/spreadsheets/d/1_qBjYd0F4BYYTxLMJjEZbQynBdHH5JGe83-U7nheJOE/edit?usp=drivesdk | 2026-08-30 | 2026-08-30 | Yes | Wed Sep 2 | Bring labor productivity toward target |  | 4d
W-005 | Finance & Office | Confirm books/reconciliations/evidence current for weekly close | Moises | Control | PUSH | Yes | No | 2026-09-04 | Open |  | No |  | https://docs.google.com/spreadsheets/d/1zrY3SOQiF2g8A_7z4ynA9mVnM7_qsvS8eBsebBRplmc/edit?usp=drivesdk | 2026-08-30 | 2026-08-30 | Yes | Fri Sep 4 | Reliable finance close / no silent issue |  | 4d
W-006 | Finance & Office | Review open creditors / obligations with Emmanuel | Moises | Follow-up | PUSH | No | No | 2026-09-03 | Open | Emmanuel | No |  | https://docs.google.com/spreadsheets/d/1zrY3SOQiF2g8A_7z4ynA9mVnM7_qsvS8eBsebBRplmc/edit?usp=drivesdk | 2026-08-30 | 2026-08-30 | Yes | Thu Sep 3 | Visibility of obligations / decisions |  | 4d
W-007 | Podcast / Legacy | Move current video/editor follow-up to next executable step | Emmanuel | Project Action | PUSH | HOLD / TEST DATA | No | 2026-09-01 | Open | Ahmad | No |  |  | 2026-08-30 | 2026-08-30 | No | Tue Sep 1 | Move production pipeline forward |  | 4d
W-008 | Ahmad Personal Finance / Life | Establish lightweight personal bills / obligations source map and weekly control | Moises | Control Build | PUSH | HOLD / TEST DATA | No | 2026-09-04 | Open |  | No |  |  | 2026-08-30 | 2026-08-30 | No | Fri Sep 4 | Personal stability / obligations visibility |  | 4d
W-009 | Ahmad Personal Finance / Life | Review subscriptions / recurring charges and surface cancellations or decisions needed | Emmanuel | Follow-up | TEST | HOLD / TEST DATA | Yes | 2026-09-02 | Open |  | No |  |  | 2026-08-30 | 2026-08-30 | No | Wed Sep 2 | Reduce unnecessary recurring outflow |  | 4d
W-010 | People / Systems | Operate Monday launch from HQ role views; confirm owners, dates, blockers and exceptions are current | Emmanuel | System Rollout | TEST | HOLD / TEST DATA | No | 2026-08-31 | Open |  | No |  |  | 2026-08-30 | 2026-08-30 | No | Mon Aug 31 | Make the operating system usable through real work |  | 4d
W-011 | My Work |  |  | Action | TEST | HOLD / TEST DATA | No |  | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  |  |  | 0d
W-012 | My Work |  |  | Action | TEST | HOLD / TEST DATA | No |  | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  |  |  | 0d
W-013 | My Work |  |  | Action | TEST | HOLD / TEST DATA | No |  | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  |  |  | 0d
W-014 | My Work | xfgnxfm | xfmfhm | Action | TEST | HOLD / TEST DATA | Yes | xmh | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  | xfmhxfhm |  | 0d
W-015 | My Work | xfgnxfm | xfmfhm | Action | TEST | HOLD / TEST DATA | Yes | xmh | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  | xfmhxfhm |  | 0d
W-016 | My Work | xfgnxfm | xfmfhm | Action | TEST | HOLD / TEST DATA | Yes | xmh | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  | xfmhxfhm |  | 0d
W-016 | My Work | xfgnxfm | xfmfhm | Action | TEST | HOLD / TEST DATA | Yes | xmh | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  | xfmhxfhm |  | 0d
W-017 | My Work | xfgnxfm | xfmfhm | Action | PUSH | Yes | Yes | xmh | Open |  | No |  |  | 2026-09-01 12:58 | 2026-09-01 12:58 | No |  | xfmhxfhm |  | 0d
Formulas:
AGE / STALE = IF([Status]="Done","Closed",IF([Last Update]="","No update",TODAY()-DATEVALUE([Last Update])&"d"))

## WEEK CLOSE — UPDATE
Control ID | Function | Control / Checklist Item | Owner | Cadence | Next Due | Status | Evidence / Link | Exception? | Notes / Next Action
C-001 | Finance & Office | Books current / posted through agreed close date | Moises | Weekly | 46269 | Open |  | No
C-002 | Finance & Office | Bank and credit-card reconciliations current | Moises | Weekly | 46269 | Open |  | No
C-003 | Finance & Office | Critical A/P and A/R reviewed | Moises | Weekly | 46269 | Open |  | No
C-004 | Finance & Office | Evidence / supporting documents confirmed | Moises | Weekly | 46269 | Open |  | No
C-005 | Edible Operations | Week Close completed and exceptions identified | Emmanuel | Weekly | 46269 | Open |  | No
C-006 | People / Systems | Critical Moves reviewed; overdue/blocked escalated | Emmanuel | Weekly | 46269 | Open |  | No
C-007 | Ahmad Personal Finance / Life | Upcoming personal bills/obligations reviewed | Moises | Weekly | 46269 | Open |  | No
C-008 | Ahmad Personal Finance / Life | Money-in / money-out and material exceptions reviewed | Moises | Weekly | 46269 | Open |  | No
C-009 | Ahmad Personal Finance / Life | Personal-finance exceptions / deadlines reviewed and escalated to Ahmad | Emmanuel | Weekly | 46269 | Open |  | No | Coordinate completeness and decisions; do not duplicate bookkeeping

## 90_SYSTEM_GUIDE (hidden)
AHMAD HQ — PHASE 1 OPERATING CORE
Purpose | One small operating backbone for work, projects/functions, recurring controls, KPIs, people/capacity, decisions, and evidence.
Operating rule | Enter once → useful to the employee → useful to Emmanuel → useful to management → retained for history.
Monday standard | Every person can see This Week / Today / Waiting On / Overdue; management sees Critical Moves, results, exceptions, capacity, decisions, and What's Next.
Drive rule | Detailed source documents and evidence stay in Drive/specialized systems; this workbook stores the management spine and links down.
PHASE 1 — WHAT STAFF USE
01_WORK_ITEMS | Primary action/task database. Add or update work here until AppSheet front end is live.
10_EMMANUEL_VIEW | Automatic working view for Emmanuel.
11_MOISES_VIEW | Automatic working view for Moises.
12_AHMAD_VIEW | Compressed management/action view for Ahmad.
03_RECURRING_CONTROLS | Weekly/monthly controls and checklists. Drill down here; roll up by exceptions.
07_REFERENCE_LINKS | One-click links to project folders, source workbooks, manuals, and evidence.
WEEKLY RHYTHM
Mon–Thu | Execute from My Week / project-function views. Update items once.
Friday | Week Close: mark completed, capture result/evidence, flag blocked/carry-forward.
Saturday | Emmanuel reviews exceptions, missing updates, capacity, KPIs, and Ahmad decisions.
Sunday | Management meeting: review v3 board; create decisions/actions directly into operating core.
Monday | New priorities/critical moves are already in each person's view.
PHASE ROADMAP
Phase 1 | Functional now: Sheets backbone + Drive links + role views + v3 management board + manual/semi-manual updates.
Phase 2 | AppSheet working interface, smart forms, filtered role/project views, automated roll-ups/alerts, standardized project setup.
Phase 3 | Full Ahmad HQ operating system: system inventory/maturity, SOPs/training, broader functions, stronger automation, audit intelligence, controlled expansion.

## 02_PROJECTS_FUNCTIONS (hidden)
Project / Function | Kind | Focus | Primary Owner | Purpose / Outcome | Current Milestone | 2–4 Key Numbers | What's Next | Primary Drive Folder / Source | Status
Edible Operations | Function | MAINTAIN | Emmanuel | Keep store stable while correcting sales/labor/service economics | Correct current sales/labor trend | Sales; Labor %; Avg Ticket; Refund/Void | Verify schedule/lead behavior effect | https://docs.google.com/spreadsheets/d/1_qBjYd0F4BYYTxLMJjEZbQynBdHH5JGe83-U7nheJOE/edit?usp=drivesdk | Active
Gardenia's Fire | Project | PUSH | Emmanuel | Prove offer and create repeatable local corporate standing-order sales | Product proof + outreach/tastings | Prospects; Contacts; Tastings; Standing Accounts; Weekly Revenue | Finalize costing, target list, outreach, tastings | https://drive.google.com/drive/folders/1-CWhZsNUR2dnbbCLLOInkSOOHtFU_utm | Active
Finance & Office | Function | PUSH | Moises | Keep books, cash, obligations, evidence, and office controls current | Reliable weekly close / exceptions | Books Current; Cash; A/P; A/R; Reconciliations; Evidence | Establish clean weekly close with evidence | https://docs.google.com/spreadsheets/d/1zrY3SOQiF2g8A_7z4ynA9mVnM7_qsvS8eBsebBRplmc/edit?usp=drivesdk | Active
Podcast / Legacy | Project | PUSH | Ahmad | Create and publish meaningful podcast/video work while retaining legacy material | Current episode/video progression | Script; Record; Review; Edit; Publish | Move next video/episode to executable step |  | Active
People / Systems | Function | MAINTAIN | Emmanuel | Clear ownership, capacity, follow-through, and system improvement | Monday-ready operating rhythm | Critical Moves; Overdue; Blocked; Capacity | Operate Phase 1 and remove duplicate reporting |  | Active
Iron Marks / Iron March | Project | PARK | TBD | Keep visible without stealing capacity until intentionally activated | Define offer/owner/test/capacity before PUSH |  | Remain parked until activation decision |  | Parked
Ahmad Personal Finance / Life | Function | PUSH | Ahmad / Moises / Emmanuel | Protect personal stability: money in/out, obligations, credit, personal admin, decisions | Basic visibility + recurring control | Money In; Money Out; Bills Due; Credit/Open Issues | Moises maintains back-end; Emmanuel coordinates completeness/exceptions; Ahmad decides |  | Build

## 04_KPI_RESULTS (hidden)
Period End | Project / Function | Metric | Target | Actual | Trend | Meaning / Exception | Source / Evidence Link | Owner
2026-08-29 | Edible Operations | Net Sales | 9300 | 7547.49 | Down | Below target |  | Emmanuel
2026-08-29 | Edible Operations | Labor % | 22% | 35.5% | Up / Bad | Materially above target |  | Emmanuel
2026-08-29 | Edible Operations | Refund + Void % |  | 3.72% |  | Elevated |  | Emmanuel
| Gardenia's Fire | Prospects Identified | [5 empty] | Emmanuel
| Gardenia's Fire | Contacts Made | [5 empty] | Emmanuel
| Gardenia's Fire | Tastings | [5 empty] | Emmanuel
| Gardenia's Fire | Standing Accounts | [5 empty] | Emmanuel
| Gardenia's Fire | Weekly Revenue | [5 empty] | Emmanuel

## 05_PEOPLE_CAPACITY (hidden)
Person | Role | Primary Functions / Projects | This Week's 3–5 Priorities | Availability / Capacity Notes | Waiting On / Constraints | Manager / Coordinator | Status
Ahmad | Owner / Final Accountability | Priorities; Decisions; Capital; Podcast; Personal | Decisions / priorities; income-producing/high-value activity; podcast | Protect decision and high-value time |  |  | Active
Emmanuel | Coordinator / Integrator | Edible; Gardenia's; People/Systems; Podcast support; office follow-through | Gardenia's; Edible correction; Finance integration; systems rollout | Current capacity to confirm | Multiple interim roles / avoid bookkeeping burden | Ahmad | Active
Moises | Finance / Bookkeeping | Finance & Office; back-end controls; evidence; selected personal-finance support | Books/reconciliations; creditors; evidence; Phase 1 back-end support | Standing schedule to confirm for this week |  | Emmanuel | Active
Viane | New Staff — Role to Confirm | Execution support — placement pending | Confirm role / availability; assign one contained responsibility with clear result | Confirm current schedule / capacity | Do not broaden until ownership and result are clear | Emmanuel | Confirm
Cathy | Edible Store Lead | Edible Operations | Store coverage; labor discipline; service; week-close execution | Tue / Thu / Fri / Sat; ~30–32 hrs/wk current known pattern — verify weekly | Schedule should align with labor target and store demand | Emmanuel | Active
Lorena | Edible Production | Edible Operations | Production continuity; quality; readiness | Current schedule to confirm | Confirm coverage and responsibilities | Cathy / Emmanuel | Active

## 06_DECISIONS (hidden)
Decision ID | Project / Function | Decision / Approval Needed | Requested By | Date Raised | Needed By | Status | Decision / Direction | Follow-up Owner | Resulting Work Item ID
D-001 | Gardenia's Fire | Confirm launch offer / pricing after product costing is complete | Emmanuel | 46264 | 46266 | Open |  | Emmanuel | W-001 / W-003
D-002 | People / Systems | Hire external Google Workspace / AppSheet integrator now? | Ahmad | 46264 | 46264 | Decided | Not yet. Continue ChatGPT-led build; revisit only if hands-on AppSheet/configuration burden warrants temporary help. | Ahmad

## 07_REFERENCE_LINKS (hidden)
Project / Function | Reference Type | Name | Google Drive / Source Link | Purpose / When to Use | Owner | Current? | Notes
AHMAD HQ | Governance | AHMAD WORKSPACE — MASTER INDEX & MAP | https://docs.google.com/document/d/1tTlyDkRx8QSacj_As6QzL4R0U3CbgP0ZwGaKUzMaTus/edit?usp=drivesdk | Workspace doorway / source map | Ahmad | Yes
AHMAD HQ | Governance | START HERE — Ahmad Workspace Protocol & AI Notes | https://docs.google.com/document/d/1srmnbnV1hzpm1_uDIzAHMa26jetuXrXojau3SaBOkp0/edit?usp=drivesdk | Rules for Drive / ChatGPT / accountability | Ahmad | Yes
Edible Operations | Operating System | Edible Hackensack — Store Operations Control System — v3 — Aug 2026 | https://docs.google.com/spreadsheets/d/1_qBjYd0F4BYYTxLMJjEZbQynBdHH5JGe83-U7nheJOE/edit?usp=drivesdk | Detailed store controls | Emmanuel | Yes
Finance & Office | Operating System | OFFICE FINANCE — LIVE CONTROL SYSTEM — REVISED Aug 2026 | https://docs.google.com/spreadsheets/d/1zrY3SOQiF2g8A_7z4ynA9mVnM7_qsvS8eBsebBRplmc/edit?usp=drivesdk | Detailed finance control layer | Moises | Yes
AHMAD HQ | Management View | Functional Management Board — v3 | https://docs.google.com/presentation/d/1Va2UIkSWL0s5wOi7MNcl7xbQONg7kE3dKpRRxlfgBCk/edit?usp=drivesdk | Sunday management presentation / current design reference | Emmanuel | Yes
AHMAD HQ | Historical Reference | AHMAD HQ — HISTORICAL SYSTEMS REFERENCE & PHASE ROADMAP — Aug 2026 | https://docs.google.com/document/d/1fBgNWXM8nKMy2_cpL96r7LbkiepiOqsBDDq66eMwby8/edit?usp=drivesdk | Phase 1/2/3 design memory and historical lessons | Ahmad | Yes
Gardenia's Fire | Project Home | Gardenia's Fire — Independent Revenue Channel | https://drive.google.com/drive/folders/1-CWhZsNUR2dnbbCLLOInkSOOHtFU_utm | Current project working folder and evidence | Emmanuel | Yes | Reuse current 2026 structure; do not create another project home

## 08_LISTS (hidden)
Owners | Priority | Status | Type | YesNo | Kind | Cadence
Ahmad | PUSH | Open | Project Action | Yes | Function | Daily
Emmanuel | MAINTAIN | In Progress | Routine Task | No | Project | Weekly
Moises | PARK | Waiting | Follow-up |  |  | Biweekly
Staff / TBD |  | Blocked | Control |  |  | Monthly
|  | Done | Decision |  |  | Quarterly
|  | Dropped | Issue |  |  | Annual
|  |  | Improvement |  |  | As Needed
Reference

## 10_EMMANUEL_VIEW (hidden)
EMMANUEL — MY WORK
Live filtered view from 01_WORK_ITEMS. Update the source row until AppSheet is live.
ID | Project / Function | Work Item / Next Action | Owner | Type | Priority | Critical Move? | Income / Result Producing? | Due Date | Status | Waiting On | Blocked? | Result / Completion Note | Evidence / Drive Link | Created / Captured | Last Update | Management Escalation?
#N/A

## 11_MOISES_VIEW (hidden)
MOISES — MY WORK
Live filtered view from 01_WORK_ITEMS. Update the source row until AppSheet is live.
ID | Project / Function | Work Item / Next Action | Owner | Type | Priority | Critical Move? | Income / Result Producing? | Due Date | Status | Waiting On | Blocked? | Result / Completion Note | Evidence / Drive Link | Created / Captured | Last Update | Management Escalation?
#N/A

## 12_AHMAD_VIEW (hidden)
AHMAD — MANAGEMENT ACTION VIEW
Only escalated / decision-sensitive / PUSH critical work. Detailed work remains below.
ID | Project / Function | Work Item / Next Action | Owner | Type | Priority | Critical Move? | Income / Result Producing? | Due Date | Status | Waiting On | Blocked? | Result / Completion Note | Evidence / Drive Link | Created / Captured | Last Update | Management Escalation?
#N/A